## Test summary report
Tester | Trần Dũng Tiến, Trần Bảo Long, Trần Anh Khôi, Nguyễn Trung Kiên, Đinh Cao Hồng Phước
Date | 2022-12-31
Summary
1 | Number of functions | 16
2 | Number of test cases | 130
3 | Number of passed test cases | 128
4 | Number of fail test cases | 2

## Bug report
Defect ID | Defect Title | Defect Description | Function ID | Severity | Reported By | Date Reported | Status | Comment
B001 | Unable to show image when add product | When Adding new product with sharp image, cant post to database because the length of base64 is too large | UC09 | Medium | Trần Dũng Tiến | 2023-01-03 | Open
B002 | Unable to show image when update profile | When updating information user with sharp image in user profile, can't patch to database because the length of base64 is too large | UC02 | Medium | Trần Dũng Tiến | 2023-01-03 | Open
B003 | Add Food To Cart | When adding food to cart in cart page. It cant update UI immediately | UC05 | Low | Trần Dũng Tiến | 2023-01-03 | Open
B004 | Database is too heavy | Database is sometimes loading too long make the user feels uncomfortable |  | High | Trần Dũng Tiến | 2023-01-03 | Open
B005 | Location | Can't show the location to help the user find the direction | UC13 | Medium | Trần Dũng Tiến | 2023-01-03 | Open
B006 | Message Feedback | Can't view the feedback message of bill in admin page | UC10 | Medium | Trần Dũng Tiến | 2023-01-03 | Open
B007 | Status Feedback | Can't view the feedback status of bill in admin page | UC10 | Medium | Trần Dũng Tiến | 2023-01-03 | Open
B008 | Change status bill | Admin can set status of the bill even it is delivered | UC10 | Low | Trần Dũng Tiến | 2023-01-03 | Open